## Stakeholder Analysis
Project Title: AI Chatbot Software Project Dates: SEP 2023 - SEP 2024 Stakeholder Organization Role Internal/External Stakeholder | Contact Person | Frequency of Comms | Power | Interest | Management Strategy Quadrant (*see lecture) | General Management Plan
| Name, Position, Email, Phone, Other Contact (preferred mode of communication in bold) | How often should you communicate with them? (Low, Medium, High) | How much power do they have to bring about a desired change on the project? (Low, High) | What is their level of interest in the project? (Low, High) | Choose from Monitor (low interest, low influence), Keep Satisfied (low interest, high influence), Keep Informed (high interest, low influence), or Manage Closely (high interest, high influence) | What is important to the stakeholder? | How could the stakeholder contribute to the project? | How could the stakeholder block the project? | Strategy for engaging the stakeholder
Fictional Company, Inc. ROLE: Project Sponsor INTERNAL | Jane Doe | High | High | High | Manage Closely | Increase the organization's productivity through the use of technology. | Ensuring the AI project has the resources it needs to be integrated with the organization's information system. | Make decision changes to halt funding or delay the project. | Biweekly discussion.
Chief Executive Officer
jdoe@fc.org
(123) 456-7890
Skype: jdoe
Fictional Company, Inc. ROLE: Stakeholder / Information Systems INTERNAL | John Doe | Medium | High | Low | Keep Informed | Ensuring the information system meets the needs of the company. | Provide insight of the current information system configuration and receommned compatible AI software. | Decides to push back on the idea of integrating AI software with the information system by arguing it would burden the IT hardware infrastructure. | Hold a monthly strategy meeting for implementing the AI software.
Information Technology Manager
jdoe1@fc.org
(123) 456-7899
Skype: jdoe1
Fictional Company, Inc. ROLE: Stakeholder / Cybersecurity INTERNAL | Jessica Johnson | Low | High | Low | Keep Satisfied | Ensuring that the company information system is safe and secure from malicious threats and data leaks. | Recommend AI software solutions that have the highest level of secure coding practices. | Can make a decision that AI software poses a threat to the infromation system due to possible data leaks. | Hold a monthly strategy meeting for implementing the AI software.
Cybersecurity Manager
jjohnson@fc.org
(123) 456-7898
Skype: jjohnson
Fictional Company, Inc. ROLE: Stakeholder / Software Testing INTERNAL | Jerry Johnson | High | Low | Low | Monitor | Ensuring the integrity of the AI software for production use. | Establish a team of software testers to conduct a rigourous testing process that includes user experience. | They may not be willing to undergo such a project if they find it to be a burden for the team. | Once the AI software has been added to the informaiton system, a weekly meeting to go over the software testing status will be implemented.
Software Test Lead
jjohnson1@fc.org
(123) 456-7897
Skype: jjohnson1
Fictional Company, Inc. ROLE: Project Manager / Software Integration INTERNAL | James Heikkinen | N/A | High | High | N/A | Goal is to integrate the AI software into the company's information system. | Leading the project of AI software integration and configure software for testing and production use. | Decides to not put in much effort to manage the stakeholders and to see the project through to the end. | Develop project plan and ensure the project meets deadlines.
Software Architect
jheikkinen@fc.org
(123) 456-7896
Skype: jheikkinen
Role: Shareholders / Investors External | N/A | High | High | High | Manage Closely | The company is profitable and is making good decisions to invest in its future. | Invest in the company or spread the news on the company's integration of AI technology. | Decide to not invest into the company if they think it is a badd move to integrate AI. | Monthly Zoom conference calls to inform the shareholders of the project status and how it will benefit the organization.
Shareholders
Shareholders List email group
N/A
Zoom Conferences

## FYI - Impact & Influence
Guiding Questions
The following are some of the lead questions to ask yourself that can be used to identify the impact and influence level of a stakeholder.
Questions
Impact
Have they had failures on previous collaborative efforts?
Is the organization hierarchical in nature, rather than being team-based?
What financial or emotional interest do they have in the outcome of your work - Is it positive or negative?
Is this project replaceable by another project?
What is their current opinion of your work? Is it based on good information?
Is it a culturally diverse population? Are there any friction among stakeholders due to this?
Are there any legal or governmental norms to be complied in executing this project?
Influence
What motivates them most of all?
What support do you want from them? Are they well placed (position in the organization) to provide this support?
What is the best way of communicating your message to them?
Who influences their opinion and who influences their opinion of you?
Do some of these influencers therefore become important stakeholders in their own right?
If they are not likely to be positive what will win them round to give their support?
If you are unlikely to win around, then how will you manage their opposition?
Have there been prior failed projects or project phases involving those people?
Have key members of the project team built trusting relationships?
Change Appetite
Do they believe that the solution will benefit the organization?
Will the benefits affect them directly?
Will the benefits be accrued elsewhere?
Are the possible negative effects of the initiative on this stakeholder greater than the rewards?
Do they believe the project team can successfully deliver the solution?
Do they see value in defining the requirements?
Do they present solutions and expect the requirements to be contained in that solution and believe that this will enable them to avoid requirements definition?
Does the organization reward collaboration?
Are personal agendas the norm?
On cross-functional efforts, do all the SMEs support the sponsor?
Are there SMEs who would prefer another sponsor?
Do they need to be educated on the solution based technology or new concept? If Yes, will a presentation or a formal training help in educating them?