## Risk Log
AI Chatbot Software Risk Log
Project Manager: James Heikkinen
Identification |  |  |  | Analysis (Issue Log) |  |  | Evaluation (Risk Log) | [7 empty] | Response Planning |  |  | Monitoring
ID | Entered by | Description | Strategy | Probability | Impact | Detectability | Exposure | Priority | [6 empty] | Mitigation Plan | Contingency Trigger | Contingency Plan | Assigned To | Status
Unique # | Name | Description of the risk and its impact | Risk Strategy: Avoid, Mitigate, Transfer, Accept | Likelihood of risk occuring | Effect on schedule, resources and/or quality | Ability to detect risk prior to causing harm to the project | Combination of probability and impact (auto-generated) | Combination of detectability and exposure (auto-generated) | probability | impact | detectability | probability + impact | exposure | detectability + exposure | Effort(s) to reduce likelihood of risk occuring or reduce the effects on the project if it does occur; include person responsible, action(s), schedule, and result | Activity, effort or date when mitigation measures are no longer effective and contingency plan should be implemented | Person responsible, action(s), schedule, resources needed | Person responsible for monitoring the risk | Open Moved to Issues Log Closed
R1 - Severe Software Vulnerabiltiy | James Heikkinen | If software contains malicious code, it increases the chance of having an information system compromise. If no solution has been impmented by vendor, than an alternative software will have to be considered. | Accept | Low | High | Medium | Medium | Medium | 1 | 3 | 2 | 4 | 2 | 4 | During the research phase of identifying the software to use, the software developers need to identify any vulnerabilites on any authoritative database sources. This prevents purchasing software that is know to be poorly coded. | When a vulnerability in the software has been discovered. | Cybersecurity and Information System stakeholders shall work with the vendor to see if a security patch can fix it. If not, work with vendor to receive a refund and look into other AI software to suit the company's needs. | Jessica Johnson | Open
R2 - High Employee Attrition Rate | James Heikkinen | Due to a competitive market for employers, employees will seek employment for more lucrative opportunities. Therefore, experienced employees can be hard to retain. | Mitigate | Medium | Medium | Low | Medium | Low | 2 | 2 | 1 | 4 | 2 | 3 | Company needs to ensure there is a program to effectively transfer knowledge from senior to junior employees. All ensure senior employees feel valued at the company via compensation and quality of life. | When the company's attrition rate is losing more people than gaining in the applicable stakeholder departments. In addition, there are knowledge gaps when implementing the software onto the information system. | Provide retention type raises for knowledge critical employees to prevent them from leaving the company. | Jane Doe | Open
R3 - Vendor Software Falsely Advertised | James Heikkinen | After purchasing, installing, and training the software, it could turn out the software does not perform as advertised. Therefore becomes a waste of financial resources. Which means more resources maybe needed if legal action is an option. | Mitigate | Low | High | Medium | Medium | Medium | 1 | 3 | 2 | 4 | 2 | 4 | Conduct research on the vendors to ensure the quality of the product. Also, identify the company's track record and any complaints made against them. | When it is discovered that the software does not provide the features that are needed for the business as it was adverstised. | Project Manager will work with the CEO to contact the vendor to get refunded. If that does not work, will have to work with legal services. Depending on the conetext, it could pause the project until this issue is resolved. | James Heikkinen | Open
R4 - Software Price Increases Significantly | James Heikkinen | Inflation or vendor pricing model changes impacts the software price significantly. 50% increase will put the project close to the budget limit. Which means a request to increase budget will have to be pursued. | Accept | Low | Medium | Medium | Low | Low | 1 | 2 | 2 | 3 | 1 | 3 | Ensure there is enough padding in the budget to prevent a price change in the software subscription that exceeds the budget. | When software pricing plan increases by 50%. | Information System stakeholder will work with vendor to negotiate price. If it is not possible, a plan to convince the CEO to increase funding for the project will be implemented. | John Doe | Open
R5 - Lack of Stakeholder Motivation | James Heikkinen | Lack of stakeholder motivation can cause a delay in the project and/or waste staff hours from lack of productivity. As a result, money is lost from extending the schedule and lack of productivity. | Mitigate | High | High | Medium | High | High | 3 | 3 | 2 | 6 | 3 | 5 | Project Sponsor (CEO) needs to encourage stakeholders to pursue this project to make the workload easier. | When it is observed that we are falling behind shedule and the root cause is the lack stakeholder support. | CEO will address the importance of the project and will ensure that this project is being held to a high priority by the applicable employees. | Jane Doe | Open
R6 - Company Cuts Budget | James Heikkinen | Company suffers negative revenue performance. Decides to cut the budget. | Accept | Medium | Medium | Medium | Medium | Medium | 2 | 2 | 2 | 4 | 2 | 4 | Pad the budget enough to prevent a significant impact that could cause the project to get cancelled. | When budget cuts are severe enough to impact the project heavily. Which should be a red flag when the budget is dropped below $200k. | Project manager will set up a presentation to inform the CEO of the importance of the project. Then, request that the budget gets revived back to its original amount or as close as it possibly can. | James Heikkinen | Open
R7 - Schedule Not Accurate | James Heikkinen | During the projects execution, it could turn out that reality paints another picture on how long it should take to inegrate the AI software into the information system. Therefore, causing more resources needed to completes the tasks. | Mitigate | Medium | Medium | Medium | Medium | Medium | 2 | 2 | 2 | 4 | 2 | 4 | Compare schedules from similar projects in the past and ensure this project's length of time required is realistic. Also, have other project managers peer review the schedule. | The project is falling behind schedule and the root cause has been identified that the estimated schedule was off. | Project manager will reassess the schedule and update it based on the miscalculation. Use the excess funds to add more resources to project to expedite later phases to get back on track. | James Heikkinen | Open
R8 - CEO Does Not Support | James Heikkinen | CEO losses interest in the project which causes it to be canceled. | Avoid | Medium | High | Medium | High | High | 2 | 3 | 2 | 5 | 3 | 5 | Have a biweekly update on the project and encourage the CEO how much this software will help the company. | CEO drops the project by cancelling it. | Project manager will set up a presentation to inform the CEO of the importance of the project. Then, request that the project gets revived and we can continue as we were. | James Heikkinen | Open
R9 - Wages Increase Significantly | James Heikkinen | Due to a competitive market for employers, employees will likely see higher wages as employers need to compete for wages. | Accept | Medium | Low | Low | Low | Low | 2 | 1 | 1 | 3 | 1 | 2 | Pad the budget enough to prevent a significant impact. | Very unlikely to increase significantly to break the budget. However, 50% increase would put the project in red flag territory. | CEO will have to increase the funds as necessary to keep the project going. | Jane Doe | Open
R10 - Budget Is Not Accurate | James Heikkinen | During the project's execution, it could turn out that the budget was under estiamted and more resources are needed to ensure the project succeeds. | Mitigate | Medium | Low | Medium | Low | Low | 2 | 1 | 2 | 3 | 1 | 3 | Compare budgets from similar projects in the past and ensure this project's staff-hours required is realistic. Also, identify software cost estimates by getting quotes from vendors. Also, have other project managers peer review the budget. | When the budget is being used u faster than expected as the project is being implemented and it is calculated to run out of funds before the project is complete. | Identify where the estimation went wrong and adjust the budget accordingly. Project manager will need to request more funding to keep the project going. | James Heikkinen | Open
R11 - Overtime Budget is Abused | James Heikkinen | Employees are abusing the overtime budget. As a result, it is eating up the resources to support the project. | Mitigate | Medium | Low | Low | Low | Low | 2 | 1 | 1 | 3 | 1 | 2 | Put in a strict rule that all overtime needs to be requested for each week. | When it has been determined that the overtime budget is being exceeded for the month(s). | Project Manager will idenitfiy root cause of why overtime is abused. Will send out an email warning employees not to abuse it. If problem still persists, apply disciplinary actions as needed. | James Heikkinen | Open
R12 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R13 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R14 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R15 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R16 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R17 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R18 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R19 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R20 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R21 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R22 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R23 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R24 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R25 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R26 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R27 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R28 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R29 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R30 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R31 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R32 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R33 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R34 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R35 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R36 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R37 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R38 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R39 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R40 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R41 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R42 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R43 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R44 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R45 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R46 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R47 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R48 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R49 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R50 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R51 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R52 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R53 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R54 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R55 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R56 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R57 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R58 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R59 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R60 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R61 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R62 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R63 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R64 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R65 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R66 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R67 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R68 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R69 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R70 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R71 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R72 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R73 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R74 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R75 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R76 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R77 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R78 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R79 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R80 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R81 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R82 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R83 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R84 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R85 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R86 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R87 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R88 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R89 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R90 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R91 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R92 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R93 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R94 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R95 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R96 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R97 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R98 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R99 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
R100 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0

## strategies (hidden)
Avoid
Accept
Transfer
Mitigate

## Issue Log (hidden)
<Project Name> Issue Log
Unique ID | Entered by | Date Logged | Description | Priority | Assigned To | Date Assigned | Action Plan(s) | Date Escalated | To Whom Escalated | Escalation Decision Due Date | Resolution Decision | Status | Date Closed (project issues) or entered into CMRS (unresolved product issues)
Unique # | Name |  | Include relationship to documented risks or other issues | Low Medium High | Person responsible for managing the issue |  | Action(s), schedule, resources needed, due dates |  |  |  |  | Open Closed
I1
I2
I3
I4
I5
I6
I7
I8
I9
I10
I11
I12
I13
I14
I15
I16
I17
I18
I19
I20
I21
I22
I23
I24
I25
I26
I27
I28
I29
I30
I31
I32
I33
I34
I35
I36
I37
I38
I39
I40
I41
I42
I43
I44
I45
I46
I47
I48
I49
I50
I51
I52
I53
I54
I55
I56
I57
I58
I59
I60
I61
I62
I63
I64
I65
I66
I67
I68
I69
I70
I71
I72
I73
I74
I75
I76
I77
I78
I79
I80
I81
I82
I83
I84
I85
I86
I87
I88
I89
I90
I91
I92
I93
I94
I95
I96
I97
I98
I99
I100

## Tables (hidden)
Open
Closed
Low
Medium
High
Open
Moved to Issues Log
Closed