## Sheet1
Week 3: Assignment - Creating the Work Breakdown Structure James Heikkinen Champlain College 17 SEP 2023 Project Title: AI Chatbot Software Project Dates: SEP 2023 - SEP 2024
Deliverables
Research AI Chatbot Software
AI Software Risk Assessment
Purchase Software
Install/Configure Software
Test Software
Deploy Software in Production Environment
| Deliverables | Tasks/Work Packages | Subtasks | Predecessors | Type
Outline Hierarchical View
1. Research AI Chatbot Software
1.1 Research AI Fundamentals (Task)
|  | 1.2 Determine if AI will meet the business needs (work package) |  | 1.1 | FF
1.2.1 Initial meeting with stakeholders to identify AI Software business needs (subtask)
1.2.2 Write up requirements for AI Software (subtask)
1.2.3 Assess if AI Software can support business operations (subtask)
|  | 1.3 Stakeholder meeting to make final approvals to proceed with AI Software integration (task) |  | 1.2 | FS
|  | 1.4 Identify AI Chatbot Software Options (work package) |  | 1.3 | FF
1.3.1 Initial stakeholder meeting to determine potential software solutions on the market (subtask)
1.3.2 Develop software comparison table (subtask)
1.3.3 Input software solution information into table (subtask)
|  | 1.5 Stakeholder meeting to eliminate software solutions that won't work (task) |  | 1.4 | FS
|  | 1.6 Get approval to proceed with risk assessment of software (task) |  | 1.5 | FS
2. AI Software Risk Assessment
|  | 2.1 Risk Assessment phase one (work package) |  | 1.6 | FF
2.1.1 Identify software vulnerabilities (subtask)
2.1.2 Identify if software vulnerabilities have been patched (subtask)
|  | 2.2 Stakeholder meeting to eliminate any risky software solutions (task) |  | 2.1 | FS
|  | 2.3 Risk Assessment phase two (work package) |  | 2.2 | FF
2.2.1 Obtain evaluation software intallation from vendors (subtask)
2.2.2 Verify hash value of software to ensure integrity (subtask)
2.2.3 Run a pre-scan of test environment servers on the status of ports/services/users/process (subtask)
2.2.4 Install AI software on separate test servers (subtask)
2.2.5 Run a post-install scan for the ports/services/users/process statuses (subtask)
2.2.6 Compare pre/post scan statuses with the applicable software on the test servers (subtask)
2.2.7 Identify any vulnerabilities or excessive changes (subtask)
|  | 2.4 Stakeholder meeting to go over results and eliminate any risky software (task) |  | 2.3 | FS
|  | 2.5 Get approval to move into the software purchase phase (task) |  | 2.4 | FS
3. Purchase Software
|  | 3.1 Contact vendors to request quotes for various software (task) |  | 2.5 | FS
|  | 3.2 Assess which software solutions fit in the budget (task) |  | 3.1 | FS
|  | 3.3 Stakeholder meeting to choose the AI Software that fits into the company's budget (task) |  | 3.2 | FS
|  | 3.4 Purchase software (task) |  | 3.3 | FS
4. Install/Configure Software
|  | 4.1 Obtain software from vendor (task) |  | 3.4 | FS
|  | 4.2 Install software (work package) |  | 4.1 | FF
4.2.1 Read installation guide and requirements (subtask)
4.2.2 Install software onto test environment (subtask)
4.2.3 Apply license to software (subtask)
|  | 4.3 Configure software (work package) |  | 4.2 | FF
4.3.1 Configure software to work on information system (subtask)
4.3.2 Connect AI software to test data (subtask)
4.3.3 Train AI software with test prompts (subtask)
4.3.4 Log all results of the AI training and software status (subtask)
|  | 4.4 Stakeholder meeting to go over AI software status (task) |  | 4.3 | FS
|  | 4.5 Get approval to move AI software into testing phase (task) |  | 4.4 | FS
5. Test Software
|  | 5.1 Develop AI software test plan and requirements (task) |  | 4.5 | FS
|  | 5.2 Brief software testers on testing plan and requirements (task) |  | 5.1 | FS
|  | 5.3 Software Testing (work package) |  | 5.2 | FF
5.3.1 Conduct software functionality testing (subtask)
5.3.2 Test for possible data leaks or vulnerabilities of software (subtask)
5.3.3 Test for user experience and design issues (subtask)
|  | 5.4 Log testing results (task) |  | 5.3 | SS
|  | 5.5 Stakeholder meeting to go over testing results (task) |  | 5.4 | FS
|  | 5.6 Get approval to implement AI software into production environament (task) |  | 5.5 | FS
6. Deploy Software into Production Environment
|  | 6.1 Install software (work package) |  | 5.6 | FF
6.1.1 Install software onto test environment (subtask)
6.1.2 Apply license to software (subtask)
|  | 6.2 Configure software (work package) |  | 6.1 | FF
6.2.1 Restrict user permissions until software is ready (subtask)
6.2.2 Configure software to work on information system (subtask)
6.2.3 Connect AI software to information system data (subtask)
6.2.4 Train AI software with prompts to enhance intelligence (subtask)
6.2.5 Log all results of the AI training and software status (subtask)
|  | 6.3 Stakeholder meeting to go over software impmentation status (task) |  | 6.2 | FS
|  | 6.4 Get approval for AI software to go live (task) |  | 6.3 | FS
|  | 6.5 Set permissions for all users to access software (task) |  | 6.4 | FS
|  | 6.6 Announce AI chatbot software to the organzization (task) |  | 6.5 | FS